## Gap Analysis
Category | Requirement (from Spec) | Status | What's Built | Gap / What's Needed | Effort
Core: Functional | Ingest files from SharePoint 2019 document library | Done | fetchLibraryItems + fetchDocumentContent via NTLM auth | None | —
Core: Functional | Supported file types: PDF, DOCX, XLSX, PPTX, SP pages, TXT | Partial | TXT, DOCX/DOC, PDF wired up; CSV and MD also handled | XLSX, PPTX, and SharePoint page text extraction not implemented. PDF parser instantiation looks buggy. | Medium
Core: Functional | RAG — answers grounded only in approved knowledge base | Partial | All documents concatenated and included in system prompt as raw text context | No real RAG (no chunking, no embeddings, no vector search). Works for small libraries; will degrade as document count grows. | High
Core: Functional | Must NOT answer from model general knowledge | Done | System prompt explicitly forbids outside knowledge; temperature=0 set | None | —
Core: Functional | Not-found fallback message (exact wording, configurable) | Done | Configurable in Settings; injected into system prompt; admin can edit via UI | None | —
Core: Functional | Citations: source document name + page/section/cell range | Partial | Title + URL cited in every response via forced Sources section | No page numbers, section headings, slide numbers, or worksheet names captured. Chunking with metadata required. | High
Core: Functional | Plain-language summary + short quoted excerpt from source | Partial | Plain-language answers enforced via system prompt | Direct quote / excerpt surfacing not in prompt or UI. Spec requires a note when a direct quote is used. | Low
Core: Functional | Session-only memory (no long-term user memory) | Not Built | Messages stored in DB across all sessions with no expiry or isolation | Need per-session scoping (sessionId) and expiry, or clear-on-close logic. | Medium
Core: Functional | No role-based access (phase 1) | Done | No auth or roles implemented | None | —
Core: Functional | No user login required (phase 1) | Done | Fully open, no login | None | —
Core: Functional | Embeddable in SharePoint 2019 via iframe / Content Editor Web Part | Done | Floating widget suitable for iframe embedding; /widget route available | None | —
Ingestion | Connect to SharePoint 2019 document library | Done | NTLM auth, site URL + library name configurable in Settings | None | —
Ingestion | File upload/replace handled through SharePoint library (not separate UI) | Done | Admin uploads to SharePoint; app syncs on demand | None | —
Ingestion | Detect added/replaced/updated files and refresh index | Partial | Sync button does a full replace (delete all + re-import) | No incremental/delta sync. No change detection by file modification date. | Medium
Ingestion | Extract text: TXT | Done | Direct UTF-8 read, capped at 8,000 chars | 8,000-char cap may truncate large files | Low
Ingestion | Extract text: DOCX / DOC | Done | mammoth library used | 8,000-char cap may truncate long documents | Low
Ingestion | Extract text: PDF | Broken | pdf-parse wired but PDFParse called as constructor incorrectly | Fix pdf-parse usage: should be pdfParse(buffer) not new PDFParse({data: buffer}) | Low
Ingestion | Extract text: XLSX (Excel) | Not Built | Returns "not supported" message | Add xlsx or exceljs package to extract cell data with sheet/cell metadata | Medium
Ingestion | Extract text: PPTX (PowerPoint) | Not Built | Returns "not supported" message | Add officeparser or pptx2json to extract slide text with slide numbers | Medium
Ingestion | Extract text: SharePoint page content | Not Built | Not implemented | Call SP REST API to fetch page content from page lists | Medium
Ingestion | Chunk content with citation metadata (file, page, section, slide, sheet) | Not Built | Content stored as one flat blob per document, truncated at 8,000 chars | Implement chunking: split by page/section/slide, store chunk metadata (page #, heading, slide #, sheet name) | High
Ingestion | Store embeddings in vector database for semantic search | Not Built | PostgreSQL stores raw text; no embeddings or vector store | Generate embeddings (Azure OpenAI text-embedding-ada-002) and store in pgvector or external vector DB | High
Ingestion | Preserve source metadata for citations | Partial | Title and URL stored per document | Need page numbers, section headings, chunk-level metadata once chunking is added | Medium
Retrieval | Semantic search over knowledge base for each query | Not Built | All documents concatenated into one prompt context block | Embed user query, vector-search top-N chunks, inject only relevant chunks into prompt | High
Retrieval | Assemble prompt with admin instructions + retrieved citations | Partial | Admin instructions + all doc content in system prompt | Replace all-docs approach with top-N retrieved chunks after vector search is built | Medium
Retrieval | Send to AI and return grounded answer with citations | Done | Azure OpenAI GPT-4o called, response returned with forced Sources section | None once retrieval is upgraded | —
Instruction Layer | Admin-editable system instruction area | Done | Custom Instructions textarea in Settings, saved to DB, applied to every chat | None | —
Instruction Layer | Controls tone, scope, fallback behavior, answer format, org-specific rules | Done | Custom instructions + separate Not Found Message + AI parameters | None | —
Instruction Layer | Configurable via UI without code changes | Done | Full Settings page at /settings | None | —
AI Model | Use Azure OpenAI (GPT) via API | Done | Azure OpenAI GPT-4o via direct fetch with AZURE_OPENAI_API_KEY env var | None | —
AI Model | Embeddings + semantic retrieval | Not Built | Not implemented | Use Azure OpenAI embeddings endpoint + vector DB (see Ingestion/Retrieval rows) | High
AI Model | Configurable model parameters (temp, top_p, max_tokens, penalties) | Done | All 5 parameters configurable in Settings, stored in DB, applied per request | None | —
AI Model | Avoid guessing / state clearly when info not found | Done | System prompt enforces this; not-found message injected | None | —
AI Model | Concise plain-language answers | Done | Enforced via system prompt rules | None | —
AI Model | Return citations with every answer | Done | Mandatory Sources section format enforced in system prompt | None | —
Security | No training on company data | Done | Azure OpenAI API — Microsoft does not train on API data by default | None | —
Security | US-only hosting | Unknown | Replit deployment geography not explicitly set | Configure deployment region to US-only when publishing | Low
Security | Documents and embeddings stored securely | Partial | PostgreSQL managed by Replit; no custom encryption at rest | When embeddings are added, ensure vector store is also US-region and encrypted | Low
Security | API keys and secrets in environment variables, not hardcoded | Done | All secrets in Replit env vars; no hardcoded keys in code | None | —
Security | Log errors; do not store sensitive conversation history beyond session | Partial | Errors logged to console; messages stored in DB indefinitely with no expiry | Add session scoping + expiry for messages table | Medium
UI | Question input | Done | Input field at bottom of chat | None | —
UI | Answer text display | Done | Markdown rendered with rehype-raw; links open in new tabs | None | —
UI | Citations displayed | Done | Sources section rendered as clickable links | None | —
UI | Note when answer includes direct quote | Not Built | No quote/excerpt indicator in UI | Add visual indicator (blockquote styling or badge) when AI returns a direct quote | Low
UI | Follow-up questions during same session | Partial | Message history shown; input always available | Conversation history NOT passed to the AI — each message answered in isolation. Need to send last N messages in API call. | Medium
UI | Clean, lightweight, embeddable | Done | Floating widget + iframe-friendly design | None | —
UI | Loading state | Done | Animated typing indicator while waiting for response | None | —
UI | Graceful error handling | Done | Error state shown in chat if request fails | None | —
UI | Fallback message shown clearly when answer not found | Done | Not-found message rendered as regular AI message in chat bubble | None | —
Admin/Config | SharePoint document library location configurable | Done | Site URL + library name in Settings | None | —
Admin/Config | OpenAI API key via environment variable | Done | AZURE_OPENAI_API_KEY in Replit secrets | None | —
Admin/Config | Editable custom system instructions | Done | Custom Instructions field in Settings | None | —
Admin/Config | Fallback response text configurable | Done | Not Found Message field in Settings | None | —
Admin/Config | Reindex / refresh action for updated documents | Done | Sync Document Library button in Settings | Delta sync is a future improvement | —
Conversation | Conversation history passed to AI for follow-up context | Not Built | Only the current single message is sent to Azure OpenAI | Include recent message history in the messages array sent to the API so AI understands follow-up questions | Low